## Team Members
Team Member | Contact Phone
Amy Hong | 907-602-8618

## Roles
Role | Team Member
Project Manager
Documentation Developer | Amy Hong
Data Warehouse Developer | Amy Hong
ETL developer | Amy Hong
Cube Developer
Report Developer | Amy Hong
Testers | Amy Hong
Release Manager

## Solution Schedule
BI Solution Projects | Est Hours | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri | Mon | Tue | Wed | Thur | Fri
Interview and Identify: | 2 | bar: Mon
Planning and Documenting: | 6 | Mon: ***; Mon: ***
Create the Data Warehouse | 2 | bar: Mon
Extract, Transform, and Load: | 4 | Mon: ****
Create Cubes: | 0
Create Reports: | 3 | Mon: ***
Test the Solution: | 2 | bar: Fri
Approve, Release, and Prepare for next version: | 1 | bar: Fri

## Estimated Hours
BI Solution Projects | Task | Action Item | Estimated Hours | Actual Hours
Interview and Identify: | Interviews | Talk To Business Owner
Talk to Mangers
Talk to Users
Talk to DBA
| Document Requirements | Create an informal overview
|  | Create a BI solution worksheet |  | 1
| Locate Data | Review database tables |  | 1
Review invoice documents
Review sales awards program
| Discuss Feasibility | Decide if the solution will work
|  |  | 2 | 2
Planning and Documenting: | Define Team Roles | What role fit this solution?
| Define Team Members | Who will fill each role?
| Define Team Schedule | When will we need them?
| Discuss Feasibility | Decide if the solution will work
| Define IT requirements | Decide which Server will we use for DW, SSIS, SSAS, SSRS
Verify a time slot of Solution automation jobs
| Define Security requirements | Decide which groups will have access to what?
| Define Licensing requirements | Verify that the company has sufficient licensing
| Estimate the cost | Hours * Wages + and additional 10% for unknowns
| Discuss Feasibility | Decide if the solution will work
| Create formal documents | Complete BI solution worksheet |  | 2
|  | Create a Development Document |  | 2
|  |  | 6 | 4
Create the Data Warehouse | Create the Database | Create the Tables |  | 1
|  | Define Constraints |  | 1
|  |  | 2 | 2
Extract, Transform, and Load: | Create ETL Code | Create a SQL Script with ETL code |  | 4
|  | Create a an SSIS package with ETL code |  | 2
|  |  | 6 | 6
Create Cubes: | Create SSAS Database | Create Dimensions
Create Cubes
Create Reports: | Create Prototype Reports | Create SSRS Reports
Create Excel Reports
|  |  | 3 | 3
Test the Solution: | Requirements | Verify naming
Verify data domains
Verify formula results
Verify presentation formatting
| Performance | Test SSIS ETL performance
Test SSAS Processing performance
Test SSRS Report performance
|  |  | 2 | 2
Approve, Release, and Prepare for next version: | Finalize formal documents | Finish development document
Create a formal overview document
Create a lessons learned document
|  |  | 1 | 1
|  | TOTAL | 24.2

## Data Warehouse
Data Warehouse Objects Worksheet
Source Object | Source Nullable | Source Type | Destination Object | Destination Nullable | Destination Type | Constraints
EnrollmentTracker.Buildings | NA | Table | Combined with DimClassrooms | NA | Table | NA
EnrollmentTracker.Buildings.BuildingID | NO | int | Combined with DimClassrooms | NO | int | NA
EnrollmentTracker.Buildings.Name | NO | nvarchar (100) | Combined with DimClassrooms | NO | nvarchar (100) | NA
EnrollmentTracker.Classrooms | NA | Table | DWEnrollmentTracker.DimClassrooms | NA | Table | NA
NA | NA | NA | DWEnrollmentTracker.DimClassrooms.ClassroomKey | NO | int | PK
EnrollmentTracker.Classrooms.BuildingID | YES | int | DWEnrollmentTracker.DimClassrooms.BuildingID | NO | int | NA
EnrollmentTracker.Classrooms.ClassroomID | NO | int | DWEnrollmentTracker.DimClassrooms.ClassroomID | NO | int | NA
EnrollmentTracker.Classrooms.Name | NO | nvarchar (100) | DWEnrollmentTracker.DimClassrooms.ClassroomName | NO | nvarchar (100) | NA
EnrollmentTracker.Buildins.Name | NO |  | DWEnrollmentTracker.DimClassrooms.BuildingsName | NO | nvarchar (100) | NA
EnrollmentTracker.Courses | NA | Table | DWEnrollmentTracker.DimCourses | NA | Table | NA
NA | NA | NA | DWEnrollmentTracker.DimCourses.CourseKey | NO | int | PK
EnrollmentTracker.Courses.CourseID | NO | int | DWEnrollmentTracker.DimCourses.CourseID | NO | int | NA
EnrollmentTracker.Courses.Name | NO | nvarchar (80) | DWEnrollmentTracker.DimCourses.CourseName | NO | nvarchar (100) | NA
EnrollmentTracker.Courses.Price | YES | Money (19,4) | DWEnrollmentTracker.DimCourses.CoursePrice | NO | decimal (19,4) | NA
EnrollmentTracker.CourseSessions | NA | Table | DWEnrollmentTracker.FactCourseSessions | NA | Table (Bridge) | NA
NA | NA | NA | DWEnrollmentTracker.FactCourseSessions.ClassroomKey | NO | int | PK, FK
NA | NA | NA | DWEnrollmentTracker.FactCourseSessions.CourseKey | NO | int | PK, FK
EnrollmentTracker.CourseSessions.ClassroomID | NO | int | Replaced by Surrogate Key | NA | NA | NA
EnrollmentTracker.CourseSessions.CourseID | NO | int | Replaced by Surrogate Key | NA | NA | NA
EnrollmentTracker.CourseSessions.Date | NO | date | DWEnrollmentTracker.FactCourseSessions.CourseSessionDate | NO | date | NA
EnrollmentTracker.CourseSessions.End | YES | int | DWEnrollmentTracker.FactCourseSessions.CourseSessionEndTimr | NO | int | NA
EnrollmentTracker.CourseSessions.Start | YES | int | DWEnrollmentTracker.FactCourseSessions.CourseSessionStartTime | NO | int | NA
EnrollmentTracker.Enrollments | NA | Table | DWEnrollmentTracker.FactEnrollments | NA | Table (Measures) | NA
EnrollmentTracker.Enrollments.CourseID | NO | int | Replaced by Surrogate Key | NA | NA | NA
EnrollmentTracker.Enrollments.EnrollmentID | NO | int | Replaced by Surrogate Key | NA | NA | NA
NA | NA | NA | DWEnrollmentTracker.FactEnrollments.CourseKey | NO | int | PK, FK
EnrollmentTracker.Enrollments.EnrollmentDate | NA | NA | DWEnrollmentTracker.FactEnrollments.EnrollmentDate | NO | date | PK, FK
EnrollmentTracker.Enrollments.EnrollmentID | NO | int | DWEnrollmentTracker.FactEnrollments.EnrollmentKey | NO | int | PK, FK
EnrollmentTracker.Enrollments.Price | NO | Money (19,4) | DWEnrollmentTracker.FactEnrollments.EnrollmentPrice | NO | decimal (19,4) | NA
NA | NA | NA | DWEnrollmentTracker.FactEnrollments.StudentKey | NO | int | PK, FK
EnrollmentTracker.Students | NA | Table | DWEnrollmentTracker.DimStudents | NA | Table | NA
NA | NA | NA | DWEnrollmentTracker.StudentKey | NO | int | PK
EnrollmentTracker.Students.Email | NO | nvarchar (55) | DWEnrollmentTracker.DimStudents.StudentEmail | NO | nvarchar (100) | NA
EnrollmentTracker.Students.FName | NO | nvarchar (70) | DWEnrollmentTracker.DimStudents.StudentName (Merged) | NO | nvarchar (200) | NA
EnrollmentTracker.Students.LName | NO | nvarchar (60) | DWEnrollmentTracker.DimStudents.StudentName (Merged) | NO | nvarchar (200) | NA
EnrollmentTracker.Students.StudentID | NO | int | DWEnrollmentTracker.DimStudents.StudentID | NO | int | NA

## ETL Objects
SSIS ETL Objects Worksheet
Object Name | Type | Description
FlushAndFillDWEnrollmentTracker.dtsx | SSIS Package | Contains Tasks and Transformation for ETL
SourceEnrollmentTracker | OLEDB Connection | Connects to the Source Database
DestinationDWEnrollmentTracker | OLEDB Connection | Connects to the Destination Database
Pre Load Sequence Container | Sequence Container | Holds Pre-Load Tasks and Data Flows
Load Dimension Table Sequence Container | Sequence Container | Holds Load Dimension Tables Tasks and Data Flows
LoadFact Tables Sequence Container | Sequence Container | Holds Load Fact Tables Tasks and Data Flows
Post Load Tasks Sequence Container | Sequence Container | Holds Post-Load Tasks and Data Flows
Drop Fks Execute SQL Task | Execute SQL Task | Drops the Foreign Keys from all tables
Clear Tables Execute SQL Task | Execute SQL Task | Truncates data from all tables and resets the autonumber (identity)
Load DimClassrooms Data Flow | Data Flow | Loads transformed data from Classrooms and Buildings to DimClassrooms
Load DimCourses Data Flow | Data Flow | Loads transformed data from Courses to DimCourses
Load DimStudents Data Flow | Data Flow | Loads transformed data from Students to DimStudents
Load FactCourseSessions Data Flow | Data Flow | Loads transformed data from CourseSessions to FactCourseSessions
Load FactEnrollments Data Flow | Data Flow | Loads transformed data from Enrollments to FactEnrollments
Replace Fks Excute SQL Task | Execute SQL Task | Replaces the Foreign Keys on all tables

## Cubes and Dimensions
SSAS Objects Worksheet
Object Name | Description